# Project status Report

# Project Summary

| ## Report Date | ## Project Name | ## Prepared By |
| --- | --- | --- |
| 23rd April, 2020 | TERMINATION PROJECT – ANALYSING THE INFLUENCE OF FARMING TECHNIQUES SUCH AS STACKING AND PULLING IN A SUCCESSFUL CAMPAIGN IN DoTA 2 | Shiva Prasad S |

# Status Summary

The development of an application which parses DoTA 2 replays and the analysis of the obtained data to track the effective usage of farming techniques is under way. The tasks performed and their statuses are listed below. The issues that aroused during the development is also listed below.

# Project Overview

| ## task | ## % Done | ## Due date | ## notes |
| --- | --- | --- | --- |
| Field Study – Understanding the paradigms and components of the game. | 100 | 5th March, 2020 | Complexity of game is very high and the components have a dynamic nature. |
| Development and Testing of replay parser. | 100 | 26th March, 2020 | The parser used by the opendota developers was modified for fulfilling the requirements of this project. |
| Analysis of JSON files that are artifacts of the parsers using python. | 70 | 16th April, 2020 | - |
| Developing an algorithm which determines the average gold and xp gain per minute. | 10 | 30th Aoril, 2020 | The dynamic nature of game is increasing the complexity of predicting the accurate gain of xp and gold. |

# Risk and issue history

| ## issue | ## ASSIGNED TO | ## DATE |
| --- | --- | --- |
| Reuse of parser – Nightstalker. There were multiple errors in parsing a replay file using this parser. The AutoValue API used in this parser had compatibility issues. | Shiva Prasad S | 12th March, 2020 |
| Reuse of parser – stats. The major issue in this parser was the servers failed to process the .dem files sent as POST request. | Shiva Prasad S | 19th March, 2020 |

# CONCLUSIONS/RECOMMENDATIONS

The project on the whole is about 65-70% completed. The tasks to be performed are compiling the analysis graph of multiple game replays and studying and improving the algorithm which determines the cutoff gold and xp gain.